## Roadmap
Workstream | Jul-Aug | late Aug | Sep | Oct | Nov | Dec
RSS Conference | Experiment design & dataset selection, Explainability analysis (SHAP/XAI) | Poster & rapid-fire preparation | RSS presentation & feedback
AIDSET Symposium | Use-case framework & benchmarking, Additional actuarial datasets | Presentation development | AIDSET presentation & feedback
BAJ Paper |  |  | Debrief and incorporate conference insights | Scoping & literature review, Foundation model benchmarking, Advanced experiments (HPC) - fine tuning/retraining? |  | Writing and Internal Review, Submission Draft
IDSC/GIRO 2027 |  |  |  | Conference targeting & positioning |  | Abstract preparation
Working Party Webpage | Structure & content plan, Initial content (TabPFN article, researcher profiles) |  | Conference outputs published |  | Ongoing maintenance
RSS title | Foundation Models, Predictive Power and Transparency in Tabular Learning |  | 5 mins lighting talk
AIDSET title | Foundation Models in Actuarial Practice: Exploring Use Cases and Value Creation |  | 20 mins presentation including Q&A

## Actions
Actions | Owner | Status | Comment
share repo w¦ max | SH | complete
review repo and standardise | SH | complete
CW to upload spanish dataset and paper | CW | complete
dataset selection: CASdatasets | CW/MO | on-track | agreed to move forward with Spanish dataset
use cases - follow the datasets (think - how do we extend beyond insurance?) | CW/MO | on-track | agreed to move forward with frequency severity models to test classifier and regressor
access to GPUs - IFoA/UCC | CW | on-track | updating funding requests to incorporate budget breakdown for submission
recruitment | CW/KG | on-track | recruitment brief with ADSWP chair for final review
find a list of foundation models and decide which works best as benchmark | CW/SH | on-track | using TabPFN for now, incorporate other models requiring GPU if funding approved
elevate SH repo rights | KG
long term aim - ADSWP benchmark on TabArena | All
CW/MO to work on candidate analysis pipeline | CW/MO
Reflect on most useful plots, stats, metrics | All
Foundation model application to reserving - illustrative analysis | KG |  | Possible nice-to-have for conferences depending on KG capacity

## Datasets
Use Case | Modelling Task | Potential CASdatasets | Comments | Suggested Dataset
Policy lapse prediction | Binary classification | eudirectlapse; uslapseagent; eusavingsurrender | avoid eudirectlapse
Claim occurrence | Binary classification | ausprivauto0405 (ClaimOcc); beMTPL97 (claim)
Claim frequency | Count regression | beMTPL16; beMTPL97; ausMTPL8486; sgautonb; freMTPL2freq | Avoid freMTPL2freq.
Claim severity | Continuous regression | itamtplcost; beaonre; besecura; freMTPL2sev | Heavy-tailed regression problem with practical pricing relevance.
Telematics pricing | Regression / Classification | catelematic13; eutelematic13; fretelematic
Catastrophe loss prediction | Regression / Extreme values | asiacomrisk; auscathist; ushurricane
Large loss modelling | Regression / Extreme values | beaonre; besecura; asiacomrisk
Reserving | Loss reserving | fre4LoBtriangles; sgtriangles; usautotriangles; usGLtriangles; swtriangles | *
Mortality modelling | Survival analysis | freMortTables; SOAGMI; ustermlife
Disability modelling | Survival analysis | freDisTables
Health insurance pricing | Regression / Classification | euhealthinsurance

## Analysis pipeline
Stage | Objective | Key Activities | RSS Focus | AIDSET Focus
1. Problem Definition | Define the actuarial prediction problem | Business objective; target variable; prediction horizon; success criteria | Statistical problem formulation | Business context and value
2. Data Understanding | Understand the dataset | Summary statistics; variable types; missing values; class balance; data quality | Data characteristics | Availability and practicality
3. Data Preparation | Create modelling dataset | Data cleaning; missing values; grouping rare levels; capping; transformations; feature engineering | Reproducible preprocessing | Real-world data preparation
4. Exploratory Data Analysis | Explore relationships | Distributions; plots; correlations; target analysis; portfolio summaries | Data insights | Portfolio understanding
5. Experimental Design | Develop robust benchmarking framework | Train/test split; cross-validation; hyperparameter tuning; evaluation metrics; reproducibility | Fair experimental methodology | Model validation process
6. Model Development | Fit candidate models | Baseline GLM; Random Forest; XGBoost/CatBoost; Foundation Model(s) | Model comparison | Practical modelling alternatives
7. Model Evaluation | Compare predictive performance | AUC; Log Loss; Brier Score; calibration; computational performance | Model performance | Business performance
8. Model Interpretation | Explain model behaviour | Coefficients; SHAP; feature importance; partial dependence; calibration plots | Explainability | Trust and governance
9. Practical Implications | Interpret findings for practitioners | Strengths; limitations; deployment considerations; governance; recommendations | Statistical conclusions | Business adoption and value
10. Sensitivity & Robustness | Test stability of conclusions | Alternative preprocessing; resampling; parameter sensitivity; repeatability; external validation (where possible) | Scientific robustness | Confidence for implementation
Let's aim to choose the same datasets and use cases for RSS and AIDSET.
Results viewed through a slightly different lens for each, Technical/Statistical side versus the actuarial practice side